## Instructions
| CE Instructions | V1.0 12/05/2020
Definition
Compensation Events are usually events which aren't the fault of the contractor which change the cost of work or time required to complete it. The Compensation Event should position the contractor in the position he was in before the event occurred. To understand if an issue is claimable as a Compensation Event, the person who wants to claim should refer to the agreed contract. Under the NEC this falls under contract clause 60. However, it may not be as simple as referring to the contract. The contract clauses can be quite vague and can be interpreted in different ways. As much information should be received from the: Site Information Pack, Drawings, Specifications, Designers and Operation team to determine if the event is claimable. For further guidance, email support@metroun.co.uk
Template Descriptions
This form should be issued to the client after Notification of a Compensation Event (NCE). The purpose is to break down the cost incurred by the contractor due to the issue encountered. This should be broken down into: Labour, Plant, Materials and Subcontractors. Once the form is complete, a senior person on the contractor side should check and approve. This will then need to be formally submitted to the client for approval.
How to use Template
The template should contain all details regarding the event and should identify all cost incurred as a result.

## Compensation Event (CE)
|  |  | Compensation Event (CE) | [5 empty] | v1.0 04/05/2020
Project name |  |  |  | CE Raised by |  |  |  | Client Reference
Project Reference |  |  |  | Original CE Value |  |  |  | CE No
Date Service Provider was made aware of event |  |  |  | Final CE Value |  | 0 |  | EWN No
Date EWN sent to Client |  |  |  | Difference |  | 0 |  | Date of CE Event
Explanation Notes - CE Narrative and justification
Location of works |  |  |  |  | Contract Clause
Location of event |  |  |  |  | Project start
Risk Register Reference |  |  |  |  | Project finish
| Cost Category |  |  |  | Quantity | Unit | Rate |  | Total
Preliminaries
Staff/ Labour
[5 empty] | 0 |  | 0 |  | 0
[7 empty] | 0 |  | 0
0
Plant
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
0
Materials
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
0
Subcontract
[7 empty] | 0 |  | 0
[7 empty] | 0 |  | 0
0
[6 empty] | Staff total including fee |  |  | 0
[6 empty] | Plant total including fee |  |  | 0
[6 empty] | Materials total including fee |  |  | 0
[6 empty] | Subcontract total including fee |  |  | 0
[7 empty] | CE Total |  | 0
Original Target Cost |  |  |  |  | This CE Total |  | 0
Previously Agreed CEs |  |  |  |  | Total Scheme CEs |  | 0
Revised Target Cost |  | 0 |  |  | Original Risk Allowance
Budget Value |  |  |  |  | Revised Risk Allowance |  | 0
Approvals
Service Provider Signature |  |  |  |  | Service Provider Authoriser Signature
Print Name |  |  |  |  | Print Name
Date |  |  |  |  | Date
Client Approval of Compensation Event
Print Name
Date